## Command Center
PFE Command Center
Merch Performance Analytics Platform ¦ Daily tracking until 2026-06-20
Days Left =DATE(2026,6,20)-TODAY() |  | Total Tasks =COUNTA(Tasks!A4:A500) | Done =COUNTIF(Tasks!F4:F500,"Done") | Critical Open =COUNTIFS(Tasks!G4:G500,"Critical",Tasks!F4:F500,"<>Done") | Late Open =COUNTIFS(Tasks!J4:J500,"Late",Tasks!F4:F500,"<>Done")
Today Focus
Use the Daily Board every morning: one technical task, one report task, one evidence/screenshot task. Update status with dropdowns and watch Deadline Health.
Status | Count
Not started
In progress
To verify
Risk

## Tasks
MASTER CHECKLIST
Track every technical, analytics, report, and defense task here
ID | Workstream | Task | Why it matters | Deliverable/Evidence | Status | Priority | Deadline | Days Left | Deadline Health | Owner | Notes
T001 | Scope & Story | Confirm final PFE title | Needed for cover page and report consistency | Final French and English title | Not started | Critical | 2026-05-13 |  |  | Hamza
T002 | Scope & Story | Freeze final PFE scope | Avoid too many late features | Confirmed scope: ETL/backend/web/mobile/OSA prediction MVP | Not started | Critical | 2026-05-14 |  |  | Hamza
T003 | Mobile App | Finish mobile dashboard KPI definitions | Mobile replaces daily report | KPI definition table + screenshot | In progress | Critical | 2026-05-15 |  |  | Hamza
T004 | Mobile App | Verify admin/supervisor login and logout | Needed for demo account switching | Admin and casa_sup tested on mobile | In progress | High | 2026-05-14 |  |  | Hamza
T005 | Data Engineering | Document Excel column mapping | Shows data engineering work | Mapping table in report | In progress | High | 2026-05-14 |  |  | Hamza
T006 | Data Engineering | Document data cleaning logic | Explains duplicate StoreCode and date parsing | Cleaning explanation + code references | In progress | High | 2026-05-14 |  |  | Hamza
T007 | Database | Prepare ER diagram | Visual proof of relational modeling | ER diagram PNG | Not started | High | 2026-05-18 |  |  | Hamza
T008 | Database | Create KPI definition SQL file | Avoid confusion in jury questions | SQL checks for stores/visits/merchandisers | In progress | High | 2026-05-18 |  |  | Hamza
T009 | Backend Spring Boot | Add professional role handling | Admin vs supervisor must be clean | Role field or documented demo logic | In progress | High | 2026-05-24 |  |  | Hamza
T010 | Backend Spring Boot | Improve login security | Spring Boot master-level feature | BCrypt password hashing; JWT only if time | Not started | High | 2026-05-24 |  |  | Hamza
T011 | Backend Spring Boot | Add validation filtering endpoint | Web needs analytical filters | Endpoint with date/rule/severity filters | Not started | High | 2026-05-26 |  |  | Hamza
T012 | Backend Spring Boot | Add merch monitoring endpoint | Core dashboard for field performance | Merch table API | Not started | High | 2026-05-27 |  |  | Hamza
T013 | Web Dashboard | Build validation issues table | Web is the place for validation results | Table with filters and details | Not started | Critical | 2026-05-27 |  |  | Hamza
T014 | Web Dashboard | Build merchandiser monitoring view | Matches internship/data analyst value | Visits/stores/coverage by merchandiser | Not started | Critical | 2026-06-01 |  |  | Hamza
T015 | Web Dashboard | Build store coverage view | Shows operational monitoring | Coverage by city/region/store | Not started | High | 2026-06-02 |  |  | Hamza
T016 | Web Dashboard | Apply Smollan branding | Professional visual identity | Logo/colors polished in web UI | Not started | Medium | 2026-06-05 |  |  | Hamza
T017 | OSA Prediction | Define OSA target variable | Prediction cannot start without target | Target definition: Oui/Non availability | Not started | Critical | 2026-05-24 |  |  | Hamza
T018 | OSA Prediction | Build OSA training dataset | ML dataset from survey_responses and visits | Training CSV/table | Not started | Critical | 2026-05-26 |  |  | Hamza
T019 | OSA Prediction | Train baseline OSA model | Advanced analytics contribution | Model metrics: accuracy, precision, recall, F1 | Not started | Critical | 2026-05-30 |  |  | Hamza
T020 | OSA Prediction | Expose OSA prediction results | Prediction must appear in demo/report | Backend endpoint + web table/card | Not started | High | 2026-06-07 |  |  | Hamza
T021 | Report Writing | Write Introduction generale | Required by school | Max 4 pages draft | Not started | Critical | 2026-05-30 |  |  | Hamza
T022 | Report Writing | Write context and existing analysis chapters | Core report body | Chapters 1 and 2 draft | Not started | Critical | 2026-06-01 |  |  | Hamza
T023 | Report Writing | Write solution/conception chapters | Explains architecture and design | Chapters 3 and 4 draft | Not started | Critical | 2026-06-03 |  |  | Hamza
T024 | Report Writing | Write realization/results chapters | Shows implementation and value | Chapters 5 and 6 draft | Not started | Critical | 2026-06-07 |  |  | Hamza
T025 | School Requirements | Prepare official cover page | Mandatory ENSAM format | Filled Page de garde_BDIoT | Not started | Critical | 2026-06-07 |  |  | Hamza
T026 | School Requirements | Write trilingual abstracts | Mandatory school requirement | Arabic/French/English abstracts under 100 words | Not started | High | 2026-06-07 |  |  | Hamza
T027 | School Requirements | Format report | Mandatory formatting rules | Times New Roman, margins, captions, TOC | Not started | Critical | 2026-06-08 |  |  | Hamza
T028 | Diagrams & Evidence | Create architecture diagram | Needed for report and defense | Architecture PNG | Not started | High | 2026-05-28 |  |  | Hamza
T029 | Diagrams & Evidence | Create ETL flow diagram | Shows Big Data pipeline | ETL PNG | Not started | High | 2026-05-28 |  |  | Hamza
T030 | Diagrams & Evidence | Capture mobile screenshots | Evidence for report | Dashboard and map screenshots | Not started | High | 2026-05-25 |  |  | Hamza
T031 | Diagrams & Evidence | Capture web screenshots | Evidence for report | Dashboard, validation, monitoring screenshots | Not started | High | 2026-06-06 |  |  | Hamza
T032 | Defense Preparation | Prepare demo script | Avoid stress during defense | Step-by-step demo guide | Not started | Critical | 2026-06-14 |  |  | Hamza
T033 | Defense Preparation | Prepare jury Q&A answers | Be ready to defend choices | Answers to 10 key questions | Not started | High | 2026-06-16 |  |  | Hamza
T034 | Defense Preparation | Prepare final presentation | Defense deliverable | PPTX slides | Not started | Critical | 2026-06-14 |  |  | Hamza
Formulas:
Days Left = IF([Deadline]="","",[Deadline]-TODAY())
Deadline Health = IF([Status]="Done","Done",IF([Deadline]="","No date",IF([Deadline]<TODAY(),"Late",IF([Deadline]-TODAY()<=3,"Urgent",IF([Deadline]-TODAY()<=7,"This week","Upcoming")))))

## Daily Board
DAILY BOARD
Open this sheet every morning, choose tasks, and write progress notes
Date | Week | Daily focus | Technical task | Report task | Evidence task | Status | Energy | Blocker | Notes
2026-05-11 | Week 1 | Scope, mobile KPIs, ETL documentation |  |  |  | Not started
2026-05-12 | Week 1 | Scope, mobile KPIs, ETL documentation |  |  |  | Not started
2026-05-13 | Week 1 | Scope, mobile KPIs, ETL documentation |  |  |  | Not started
2026-05-14 | Week 1 | Scope, mobile KPIs, ETL documentation |  |  |  | Not started
2026-05-15 | Week 1 | Scope, mobile KPIs, ETL documentation |  |  |  | Not started
2026-05-16 | Week 1 | Scope, mobile KPIs, ETL documentation |  |  |  | Not started
2026-05-17 | Week 1 | Scope, mobile KPIs, ETL documentation |  |  |  | Not started
2026-05-18 | Week 2 | Data model, backend, OSA dataset definition |  |  |  | Not started
2026-05-19 | Week 2 | Data model, backend, OSA dataset definition |  |  |  | Not started
2026-05-20 | Week 2 | Data model, backend, OSA dataset definition |  |  |  | Not started
2026-05-21 | Week 2 | Data model, backend, OSA dataset definition |  |  |  | Not started
2026-05-22 | Week 2 | Data model, backend, OSA dataset definition |  |  |  | Not started
2026-05-23 | Week 2 | Data model, backend, OSA dataset definition |  |  |  | Not started
2026-05-24 | Week 2 | Data model, backend, OSA dataset definition |  |  |  | Not started
2026-05-25 | Week 3 | Web validation, merch monitoring, OSA baseline model |  |  |  | Not started
2026-05-26 | Week 3 | Web validation, merch monitoring, OSA baseline model |  |  |  | Not started
2026-05-27 | Week 3 | Web validation, merch monitoring, OSA baseline model |  |  |  | Not started
2026-05-28 | Week 3 | Web validation, merch monitoring, OSA baseline model |  |  |  | Not started
2026-05-29 | Week 3 | Web validation, merch monitoring, OSA baseline model |  |  |  | Not started
2026-05-30 | Week 3 | Web validation, merch monitoring, OSA baseline model |  |  |  | Not started
2026-05-31 | Week 3 | Web validation, merch monitoring, OSA baseline model |  |  |  | Not started
2026-06-01 | Week 4 | Prediction results, screenshots, first report draft |  |  |  | Not started
2026-06-02 | Week 4 | Prediction results, screenshots, first report draft |  |  |  | Not started
2026-06-03 | Week 4 | Prediction results, screenshots, first report draft |  |  |  | Not started
2026-06-04 | Week 4 | Prediction results, screenshots, first report draft |  |  |  | Not started
2026-06-05 | Week 4 | Prediction results, screenshots, first report draft |  |  |  | Not started
2026-06-06 | Week 4 | Prediction results, screenshots, first report draft |  |  |  | Not started
2026-06-07 | Week 4 | Prediction results, screenshots, first report draft |  |  |  | Not started
2026-06-08 | Week 5 | Formatting, review, defense preparation |  |  |  | Not started
2026-06-09 | Week 5 | Formatting, review, defense preparation |  |  |  | Not started
2026-06-10 | Week 5 | Formatting, review, defense preparation |  |  |  | Not started
2026-06-11 | Week 5 | Formatting, review, defense preparation |  |  |  | Not started
2026-06-12 | Week 5 | Formatting, review, defense preparation |  |  |  | Not started
2026-06-13 | Week 5 | Formatting, review, defense preparation |  |  |  | Not started
2026-06-14 | Week 5 | Formatting, review, defense preparation |  |  |  | Not started
2026-06-15 | Week 6 | Final freeze and rehearsal |  |  |  | Not started
2026-06-16 | Week 6 | Final freeze and rehearsal |  |  |  | Not started
2026-06-17 | Week 6 | Final freeze and rehearsal |  |  |  | Not started
2026-06-18 | Week 6 | Final freeze and rehearsal |  |  |  | Not started
2026-06-19 | Week 6 | Final freeze and rehearsal |  |  |  | Not started
2026-06-20 | Week 6 | Final freeze and rehearsal |  |  |  | Not started

## Weekly Plan
WEEKLY EXECUTION PLAN
Deadlines from May 11 to June 20
Week | Dates | Objective | Must Finish | Main Risk | Status
Week 1 | 2026-05-11 to 2026-05-17 | Stabilize scope and mobile/dashboard basics | PFE title, KPI definitions, admin/supervisor login, report outline | Changing scope every day | In progress
Week 2 | 2026-05-18 to 2026-05-24 | Strengthen data model and backend | ER diagram, ETL mapping, backend filters, OSA target | Authentication consumes too much time | Not started
Week 3 | 2026-05-25 to 2026-05-31 | Web analytics and OSA prediction base | Validation table, merch monitoring, OSA dataset/model | Web dashboard not stable | Not started
Week 4 | 2026-06-01 to 2026-06-07 | Final feature package and report draft | Prediction results, screenshots, first full report draft | Report delayed | Not started
Week 5 | 2026-06-08 to 2026-06-14 | Polish and review | Formatted report, annexes, presentation, demo script | Feedback arrives late | Not started
Final Week | 2026-06-15 to 2026-06-20 | Final delivery and defense readiness | Freeze code, final PDF/PPTX, rehearsal | Last minute bugs | Not started

## School Requirements
SCHOOL REQUIREMENTS
ENSAM PFE report requirements to check before delivery
Requirement | Expected Deliverable | Status | Deadline | Deadline Health | Notes
Official cover page | Use Page de garde_BDIoT.docx | Not started | 2026-06-07
Company signature | Signed report page or approval | Not started | 2026-06-12
Trilingual abstracts | Arabic, French, English, max 100 words each | Not started | 2026-06-07
Keywords | 5 to 8 keywords | Not started | 2026-06-07
Table of contents | Paginated, 1 to 2 pages | Not started | 2026-06-05
Introduction generale | Max 4 pages | Not started | 2026-05-30
Background/theory | 5 to 10 pages | Not started | 2026-05-31
Problem statement | 5 to 10 pages | Not started | 2026-06-01
Retained solution | 2 to 3 pages | Not started | 2026-06-01
Adopted solution and algorithms | 5 to 10 pages | Not started | 2026-06-02
Realization section | 2 to 5 pages | Not started | 2026-06-03
Chronogram | 1 to 2 pages | Not started | 2026-06-04
Conclusion and perspectives | 1 to 2 pages | Not started | 2026-06-06
Bibliography | 1 to 3 pages | Not started | 2026-06-06
Formatting | Times New Roman, margins, captions, justified text | Not started | 2026-06-08
Formulas:
Deadline Health = IF([Status]="Done","Done",IF([Deadline]="","No date",IF([Deadline]<TODAY(),"Late",IF([Deadline]-TODAY()<=3,"Urgent",IF([Deadline]-TODAY()<=7,"This week","Upcoming")))))

## OSA Prediction
OSA PREDICTION MVP
Keep this simple: an academic predictive analytics module with clear metrics
Step | Task | Business Meaning | Technical Approach | Status | Deadline | Deadline Health
1 | Define target variable | Predict product availability Oui/Non | Use OSA survey response as target | Not started | 2026-05-24
2 | Build dataset | Create historical learning table | Join survey_responses + visits + stores + products | Not started | 2026-05-26
3 | Feature engineering | Capture store/product/context effects | Store, product, brand, category, city, region, day, history | Not started | 2026-05-27
4 | Train baseline model | First prediction result | Logistic Regression or Random Forest | Not started | 2026-05-30
5 | Evaluate model | Prove model quality | Accuracy, precision, recall, F1, confusion matrix | Not started | 2026-06-01
6 | Store predictions | Make result usable by dashboard | CSV/table with risk level | Not started | 2026-06-03
7 | Expose API | Connect ML to app | Spring Boot endpoint for predictions | Not started | 2026-06-05
8 | Web view | Show analytics value | High-risk out-of-stock products table/card | Not started | 2026-06-07
Formulas:
Deadline Health = IF([Status]="Done","Done",IF([Deadline]="","No date",IF([Deadline]<TODAY(),"Late",IF([Deadline]-TODAY()<=3,"Urgent",IF([Deadline]-TODAY()<=7,"This week","Upcoming")))))

## Jury Q&A
JURY-READY QUESTIONS
Prepare these answers before the defense
Question | Answer Direction | Status | Notes
Why StoreCode and not StoreName? | StoreName is not unique; StoreCode is the business key. | To verify | Use Excel duplicate example.
Why mobile and web? | Mobile is operational daily monitoring; web is analytical validation and decision support. | To verify
Why MySQL? | Relational integrity, joins, structured reporting, familiar enterprise database. | To verify
Why Spring Boot? | Professional REST API layer, separation of concerns, scalable backend architecture. | To verify
Why Python ETL? | Pandas is efficient for Excel cleaning, transformation, and analytics preparation. | To verify
What is Big Data/analytics value? | ETL, data quality, KPI monitoring, validation, OSA prediction. | To verify
What are limits? | Data quality, demo authentication, prediction depends on historical data volume. | To verify
Future work? | JWT auth, richer ML, real-time pipeline, Docker, CI/CD, cloud deployment. | To verify

## Evidence
DEMO & REPORT EVIDENCE
Screenshots, diagrams, SQL outputs, and API examples to collect
Evidence Item | Where Used | Status | Deadline | Deadline Health | File/Link | Notes
Architecture diagram | Report + presentation | Not started | 2026-05-28
ETL flow diagram | Report + presentation | Not started | 2026-05-28
Database ER diagram | Report | Not started | 2026-05-29
Mobile dashboard screenshot | Report + presentation | Not started | 2026-05-25
Mobile map screenshot | Report + presentation | Not started | 2026-05-25
Web validation dashboard screenshot | Report + presentation | Not started | 2026-06-06
Merch monitoring dashboard screenshot | Report + presentation | Not started | 2026-06-06
OSA prediction metrics screenshot/table | Report + presentation | Not started | 2026-06-08
API JSON examples | Annex | Not started | 2026-06-10
SQL validation examples | Annex | Not started | 2026-06-10
Final demo script | Defense | Not started | 2026-06-14
Formulas:
Deadline Health = IF([Status]="Done","Done",IF([Deadline]="","No date",IF([Deadline]<TODAY(),"Late",IF([Deadline]-TODAY()<=3,"Urgent",IF([Deadline]-TODAY()<=7,"This week","Upcoming")))))

## Report Plan
REPORT STRUCTURE
Use this to track writing progress chapter by chapter
Section | Content | Target Pages | Status | Deadline | Deadline Health | Notes
Page de garde | Official BDIoT template | 1 | Not started | 2026-06-07
Remerciements | Thanks to ENSAM, Smollan, supervisors | 1 | Not started | 2026-06-07
Resume trilingue | Arabic, French, English abstracts and keywords | 1-2 | Not started | 2026-06-07
Introduction generale | Context, motivation, objectives, methodology | Max 4 | Not started | 2026-05-30
Chapitre 1 | Smollan, Unilever project, retail execution context | 5-10 | Not started | 2026-05-31
Chapitre 2 | Manual process, Excel exports, data quality problems | 5-10 | Not started | 2026-06-01
Chapitre 3 | Proposed solution, architecture, technology choices | 2-3 | Not started | 2026-06-02
Chapitre 4 | Design: database, ETL, API, validation, UI | 5-10 | Not started | 2026-06-03
Chapitre 5 | Implementation and screenshots | 2-5 | Not started | 2026-06-05
Chapitre 6 | Results, dashboards, validation, OSA prediction | 4-8 | Not started | 2026-06-07
Conclusion | Achievements, limits, perspectives | 1-2 | Not started | 2026-06-08
Bibliography | References | 1-3 | Not started | 2026-06-08
Annexes | SQL, API, screenshots, setup guide | As needed | Not started | 2026-06-10
Formulas:
Deadline Health = IF([Status]="Done","Done",IF([Deadline]="","No date",IF([Deadline]<TODAY(),"Late",IF([Deadline]-TODAY()<=3,"Urgent",IF([Deadline]-TODAY()<=7,"This week","Upcoming")))))

## Lists (hidden)
Status | Priority | Deadline Health
Not started | Critical | Done
In progress | High | Late
To verify | Medium | Urgent
Done | Low | This week
Blocked |  | Upcoming
Risk |  | No date